## Sheet1
Pipe Cleaner - Overall Progress
Kirkland Lab Site
Total TRRs - 30
August 12, 2020 - 09:15 AM
Pipes | PM Stage | Status | Tech Stage | Status | VSS Stage | Status | Engineer | Status
1 | COMPLETD | Ready for Tech | COMPLETD | Ready for VSS | UNDERWAY | 45% - Manual Testing
2 | COMPLETD | Ready for Tech | BLOCKER | 35 % - Missing Parts
3 | UNDERWAY | 25 % - CRD Review
4 | COMPLETD | Ready for Tech | COMPLETD | Ready for VSS | COMPLETD | Ready for Engineer | UNDERWAY | 40 % - Writing Qual Report
5 | BLOCKER | 10 % - Need CRD
6 | COMPLETD | Ready for Tech | COMPLETD | Ready for VSS | COMPLETD | Ready for Engineer | COMPLETD | Report Generated
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30